## Gantt
Quadcopter 2015 | [8 empty] | Version 1.0 | time axis 2015-07-06 to 2016-07-03
[10 empty] | 2015 | [6 empty] | 2015 | [6 empty] | 2015 | [6 empty] | 2015 | [6 empty] | 2015 | [6 empty] | 2015 | [6 empty] | 2015 | [6 empty] | 2015 | [6 empty] | 2015 | [6 empty] | 2015 | [6 empty] | 2015 | [6 empty] | 2015 | [6 empty] | 2015 | [6 empty] | 2015 | [6 empty] | 2015 | [6 empty] | 2015 | [6 empty] | 2015 | [6 empty] | 2015 | [6 empty] | 2015 | [6 empty] | 2015 | [6 empty] | 2015 | [6 empty] | 2015 | [6 empty] | 2015 | [6 empty] | 2015 | [6 empty] | 2015 | [6 empty] | 2015 | [6 empty] | 2016 | [6 empty] | 2016 | [6 empty] | 2016 | [6 empty] | 2016 | [6 empty] | 2016 | [6 empty] | 2016 | [6 empty] | 2016 | [6 empty] | 2016 | [6 empty] | 2016 | [6 empty] | 2016 | [6 empty] | 2016 | [6 empty] | 2016 | [6 empty] | 2016 | [6 empty] | 2016 | [6 empty] | 2016 | [6 empty] | 2016 | [6 empty] | 2016 | [6 empty] | 2016 | [6 empty] | 2016 | [6 empty] | 2016 | [6 empty] | 2016 | [6 empty] | 2016 | [6 empty] | 2016 | [6 empty] | 2016 | [6 empty] | 2016 | [6 empty] | 2016
Start | 2015-07-01
Today | 2015-07-12
ID | Task Description |  | Start Date | Planned End Date | Actual End Date | Work Days Planned | Work Days Elapsed | Work Days Remain | Work Days Overrun | time axis 2015-07-06 to 2016-07-03
1 | Controller | WHO ?? | 2015-07-20 | 2015-07-31 |  | 10 | 0 | 10 | 0
1.1 | Board nhận UART control 6 PWM | Tuấn | 2015-07-20 | 2015-07-24 |  | 5 | 0 | 5 | 0
1.2 | Bay thử | Tuấn | 2015-07-27 | 2015-07-31 |  | 5 | 0 | 5 | 0
1.3 | Mua controller + RCV | Tuấn | 2015-07-27 | 2015-07-31 |  | 5 | 0 | 5 | 0
2 | ĐỌC SOURCE KK2 |  | 2015-07-19 | 2015-08-08 |  | 15 | 0 | 15 | 0
2.1 | Code phần điều khiển, nhận tín hiệu điều khiển | Tuấn | 2015-07-26 | 2015-08-08 |  | 10 | 0 | 10 | 0
2.2 | Code điều khiển động cơ. Xem nó hoạt động như thế nào. | Tài | 2015-07-19 | 2015-07-25 |  | 5 | 0 | 5 | 0
2.3 | Code cho LCD | Linh | 2015-07-20 | 2015-07-25 |  | 5 | 0 | 5 | 0
2.3 | Code cảm biến nghiêng | Tài | 2015-07-19 | 2015-07-31 |  | 10 | 0 | 10 | 0
2.4 | Code PID, Matlab + simulink | Linh | 2015-08-04 | 2015-09-02 |  | 22 | 0 | 22 | 0
2.4 | Code cho bộ lọc | Tài | 2015-07-26 | 2015-08-01 |  | 5 | 0 | 5 | 0
3 | PHÁT TRIỂN BOARD |  | 2015-08-01 | 2015-08-30 |  | 20 | 0 | 20 | 0
2.1 | Chọn VDK + IMU |  | 2015-08-02 | 2015-08-31 |  | 21 | 0 | 21 | 0
Debug bằng máy tính. Giao diện
2.2 | Code IMU mới |  | 2015-08-03 | 2015-09-01 |  | 22 | 0 | 22 | 0
2.3 | Code PWM mới |  | 2015-08-04 | 2015-09-02 |  | 22 | 0 | 22 | 0
2.3 | Code bộ nhận mới |  | 2015-08-04 | 2015-09-02 |  | 22 | 0 | 22 | 0
2.4 | Kết hợp code |  | 2015-08-04 | 2015-09-02 |  | 22 | 0 | 22 | 0
2.4 | Bay thử |  | 2015-08-05 | 2015-09-03 |  | 22 | 0 | 22 | 0
Tránh vật cản
Tìm hiểu các board xử lý ảnh. (raspherry pi, intel geogile)
Tìm đường bằng google map
Note on B6: Author: Bay xem chơi
Note on B10: Author: Hiểu và làm chủ source code
Note on B15: Author: Mô hình máy bay trên máy tinh. Hiểu các thông số điều khiển. Khả năng của Matlab
Note on B17: Author: Giữ nguyên code của PID, Filter. Code mới phần nhận dữ liệu IMU, và bộ nhận.
Note on B25: Author: Sau bước này sẽ làm chủ phần mềm và phần cứng

## Settings (hidden)
Name | Value | Description
DateOffset | 1 | Used by the scrollbar. Do not manually change.
WeekStartType | 2 | Sets the day of the week to display as the start of the week (e.g. 2 = Monday).
GanttNoOfYears | 2 | Sets the date coverage of the Gantt chart (i.e. the latest date that can be displayed).
ShowFY | FALSE | Toggles between splitting years into Financial Years (e.g. 2009/10) or Calendar Years (e.g. 2009). Set to TRUE if you want to display Financial Years.